## Team Hours
Team Working Hours
[ MATS SW Team ]
Product | Project Name | Activity | Hours / h | Lead | Support | Remark
E-Compressor | Honda 28M | SWE1. Requiremnet Analysis | 200 | Lilong Xu | Jason Zhang
|  | SWE2. Architecture Design | 200 | Jason Zhang | Bin Huang
|  | SWE3. Development | 200 |  |  | Done by supplier.
|  | SWE4. Unit Test | 200 |  |  | Done by supplier.
|  | SWE5. Integration Test | 200 |  |  | Done by supplier.
|  | SWE6. Qualification Test | 200 | Bin Huang | Jason Zhang
|  | Debug | 200 | Jason Zhang
|  | Documentaion | 200 | Bin Huang
|  | DV Support | 200 | Bin Huang
|  | PV Support | 200 | Bin Huang
EOL Support
| 36CC Platform | SWE1. Requiremnet Analysis | 200
|  | SWE2. Architecture Design | 200
|  | SWE3. Development | 200
|  | SWE4. Unit Test | 200
|  | SWE5. Integration Test | 200
|  | SWE6. Qualification Test | 200
Debug
|  | Documentaion | 200
|  | DV Support | 200
|  | PV Support | 200
|  | EOL Support | 200
E-Pump | VW-Ecomp | SWE1. Requiremnet Analysis | 200
|  | SWE2. Architecture Design | 200
|  | SWE3. Development | 200
|  | SWE4. Unit Test | 200
|  | SWE5. Integration Test | 200
|  | SWE6. Qualification Test | 200
Debug
|  | Documentaion | 200
|  | DV Support | 200
|  | PV Support | 200
|  | EOL Support | 200
| xxx | SWE1. Requiremnet Analysis | 200
|  | SWE2. Architecture Design | 200
|  | SWE3. Development | 200
|  | SWE4. Unit Test | 200
|  | SWE5. Integration Test | 200
|  | SWE6. Qualification Test | 200
|  | Documentaion | 200
|  | DV Support | 200
|  | PV Support | 200
|  | EOL Support | 200
| Non-Project Task | Study | 200
|  | Training | 200
|  | Documentation | 200
|  | Development | 200
Process Improvement
Toolchain Development
Requirement Analysis

## VW
VW
MAHLE Automotive Technologies (Suzhou) Co., Ltd. | [5 empty] | Display_Week | 5 | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04
[6 empty] | START WORKING DATE | 2025-07-01 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10
Activity | Task Name | Start Date | End Date | Duration / d | Status | Owner | Comment | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Acquisition
SWE1. Requiremnet Analysis | Review Requirements | 2025-07-18 | 2025-07-24 | 5 | In Progress | Min Xiong
Return

## P-Honda 28M
Honda 28M
MAHLE Automotive Technologies (Suzhou) Co., Ltd. | [5 empty] | Display_Week | 2 | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04
[6 empty] | START WORKING DATE | 2025-07-01 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10
Activity | Task Name | Start Date | End Date | Duration / d | Status | Owner | Comment | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
B Sample
SWE1. Requiremnet Analysis | 与HET评审CAN通讯通用需求 | 2025-07-16 | 2025-07-16 | 1 | Done | Jason Zhang | Min Xiong Support
SWE1. Requiremnet Analysis | Review网络安全附件9 RISK RANK | 2025-07-17 | 2025-07-18 | 2 | Done | Min Xiong | Jason Support
Documentaion | 向Honda提供CAN一致性说明材料 | 2025-07-12 | 2025-07-23 | 9 | In Progress | Jason Zhang
Documentaion | 向Dewey提供B样软件测试计划 | 2025-07-14 | 2025-07-14 | 1 | Done | Jason Zhang | 07/15：已根据Bin的反馈更新了测试计划
Documentaion | 向HET反馈静态代码分析报告格式是否可行 | 2025-07-18 | 2025-07-18 | 1 | In Progress | Jason Zhang
Documentaion | 确认当前HET实施的软件最新版DBC | 2025-07-16 | 2025-07-16 | 1 | Done | Jason Zhang | 0526版EXCEL
SWE1. Requiremnet Analysis | 与HET评审电机空转，堵转，缺相故障诊断 | 2025-07-17 | 2025-07-17 | 1 | Done | Lilong Xu | Min Xiong, Jason Support
SWE1. Requiremnet Analysis | 与Honda沟通CAN通用需求技术参数 | 2025-07-23 | 2025-07-23 | 1 | Done | Jason Zhang
SWE1. Requiremnet Analysis | 与Honda澄清网络安全需求 | 2025-07-23 | 2025-07-23 | 1 | Done | Jason Zhang
Documentaion | 更新诊断列表 | 2025-07-23 | 2025-07-24 | 2 | In Progress | Bin Huang
Return

## P-36CC Platform
36CC Platform
MAHLE Automotive Technologies (Suzhou) Co., Ltd. | [5 empty] | Display_Week | 5 | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04
[6 empty] | START WORKING DATE | 2025-07-01 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10
Activity | Task Name | Start Date | End Date | Duration / d | Status | Owner | Comment | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
B Sample
SWE1. Requiremnet Analysis | Review释放给首智的需求 | 2025-07-24 | 2025-07-28 | 3 | Done | Jason Zhang | Min Xiong Support
Return

## Non-Project_Task
Non-Project Task
MAHLE Automotive Technologies (Suzhou) Co., Ltd. | [5 empty] | Display_Week | 2 | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04
[6 empty] | START WORKING DATE | 2025-07-01 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10
Activity | Task Name | Start Date | End Date | Duration / d | Status | Owner | Comment | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Toolchain Development | Motor Dyne Bench Solution | 2025-07-24 | 2025-07-28 | 3 | Not Start | Bin Huang
Toolchain Development | Online Working Hours System | 2025-07-11 | 2025-08-06 | 19 | In Progress | Feihao Liu
Development | Model Reference SW Architecture | 2025-07-23 | 2025-07-25 | 3 | In Progress | Shenglin Chen
Requirement Analysis | Analyze requirement on PPE | 2025-07-28 | 2025-08-29 | 25 | Not Start | Min Xiong
Process Improvement | SW Joint Development Process | 2025-07-24 | 2025-07-24 | 1 | In Progress | Jason Zhang
Return

## Team
Team Members
Name | Site | Competency | Title | Mobile | E-mail Address | Resposible
Lilong Xu | MATS | SW | Software Manager |  | lilong.xu@mahle.com
Alex Li | MATS | SW | Software Engineer | 18503397615 | alex.a.li@mahle.com
Alex Zhu | MATS | SW | Software Engineer |  | alex.zhu@mahle.com
Bin Huang | MATS | SW | Software Engineer |  | bin.b.huang@mahle.com
Feihao Liu | MATS | SW | Software Engineer | 18846016903 | feihao.liu@mahle.com
Jason Zhang | MATS | SW | Software Engineer | 18993573429 | jason.c.zhang@mahle.com
Longhui Lai | MATS | SW | Software Engineer | 15751018155 | longhui.lai@mahle.com
Libo Zhu | MATS | SW | Software Engineer | 18651181168 | libo.zhu@mahle.com
Mingyu Ma | MATS | SW | Software Engineer | 17315372380 | mingyu.ma@mahle.com
Min Xiong | MATS | SW | Software Engineer | 13313843160 | min.xiong@mahle.com
Shenglin Chen | MATS | SW | Software Engineer | 18662237910 | shenglin.chen@mahle.com
Stephen Zeng | MATS | SW | Software Engineer | 18166038355 | stephen.zeng@mahle.com
Xin Guo | MATS | SW | Software Engineer |  | xin.guo@mahle.com

## Holidays & Special Days (hidden)
Holidays and other Non-working Days
Dolidays Date | Adjustments | Description
2025-01-01 |  | 元旦
2025-01-28 | 2025-01-26 | 春节
2025-01-29 | 2025-02-08 | 春节
2025-01-30 |  | 春节
2025-01-31 |  | 春节
2025-02-01 |  | 春节
2025-02-02 |  | 春节
2025-02-03 |  | 春节
2025-02-04 |  | 春节
2025-04-04 |  | 清明
2025-04-05 |  | 清明
2025-04-06 |  | 清明
2025-05-01 | 2025-04-27 | 劳动节
2025-05-02 |  | 劳动节
2025-05-03 |  | 劳动节
2025-05-04 |  | 劳动节
2025-05-05 |  | 劳动节
2025-05-31 |  | 端午节
2025-06-01 |  | 端午节
2025-06-02 |  | 端午节
2025-10-01 | 2025-09-28 | 国庆节
2025-10-02 | 2025-10-11 | 国庆节
2025-10-03 |  | 国庆节
2025-10-04 |  | 国庆节
2025-10-05 |  | 国庆节
2025-10-06 |  | 国庆节，中秋节
2025-10-07 |  | 国庆节
2025-10-08 |  | 国庆节